## WBS
AI-Integrated Custom Application Development Method |  | * Activities in blue font represent the AI-specific ones
Phase | Activity | Participants | Deliverables
AI Strategy & Feasibility Analysis | Identify AI Use Case | Business Analyst (BA), Product Owner, Client SMEs, Data Scientist | AI Use Case Document
| Conduct Feasibility Study | BA, Product Owner, Client SMEs | Feasibility Report
| Assess AI Readiness | BA, Data Scientist, Client SMEs | AI Readiness Report
| Assess Data Privacy & Compliance | BA, Ethics Auditor, Client SMEs | Compliance Assessment Report
| Determine Data Requirements and Success Criteria | BA, Product Owner, Client SMEs | Data Requirements Report
Requirements Phase | Conduct project initiation and kickoff meetings | Delivery Manager (DM), Business Analyst (BA) | Kickoff Presentation
| Identify and engage key stakeholders | DM, BA | Stakeholder List, RACI Matrix
| Conduct stakeholder interviews and workshops | BA, Client SMEs, Client Owner | Stakeholder Requirements
| Elicit business requirements from stakeholders | BA, Client SMEs | Business Requirements Document (BRD)
| Define AI-Specific Requirements | BA, Data Scientist, Product Owner | AI BRD (incl. Use Cases, Data Needs)
| Define AI Model Compliance Requirements | BA, Ethics Auditor, Client SMEs | Compliance Requirements Document
| Review and finalize BRD internally | BA, BA Manager | Reviewed BRD
| Obtain formal approval of BRD from stakeholders | DM, BA, Client Owner | Signed-off BRDs
| Identify functional and non-functional requirements | BA, Architect | Non-Functional Requirements (NFRs)
| Prioritize requirements with stakeholders | BA, DM, Product Owner | Prioritized Requirement List
| Create UI Wireframes as per prioritization | BA, Architect | Draft UI Wireframes
| Present Wireframes to Clients and obtain concurrence | BA, Client SMEs, Client Owner | Final UI Wireframes
| Document Functional Specs incl. User Stories, UI in iterations | BA, Product Owner | Functional Specification Document (FSD)
| Review and finalize FSD internally | BA, BA Manager, Architect | Reviewed FSD
| Create and finalize the Requirements Traceability Matrix (RTM) | BA | RTM Document
| Obtain formal approval of FSD from stakeholders in iterations | DM, BA, Client Owner | Signed-off FSDs
| Define/ Confirm change control process for requirements | DM, Change Control Board (CCB) | Change Control Plan
| Conduct requirements handover to design team | BA, Tech Lead (TL) | Handover Minutes
Design Phase | Create Architecture Document for entire application | Architect | System Architecture Document (SRD)
| Walk-through and fine-tunning of SRD | Architect, TLs | Final SRD
| Create High Level Design (HLD) Document for entire application | TLs | High Level Design (HLD)
| Create High Level Design of AI Model | Data Scientist, AI/ML Engineer, Architect | AI HLD (AI Model Design & Algorithm, Model Integration, Data Flow, Explainability & Interpretability)
| Walk-through and fine-tunning of HLD | Architect, TLs | Final HLD
| Create Test Plan including Test Strategy | Test Manager | Test Strategy & Plan (TSP)
| Walk-through and fine-tunning of TSP | Test Manager, Architect, Tester | Final TSP
| Requirement (BRD/ FSD) Self Study & Walkthrough | BA, TL, Developer, Tester | BRD, FSD
| Apportion features to planned development iterations | TL | Iteration Plan & Tracker
| Create/ update UI Wireframes & update FSD | BA, UI Developer | Updated UI Wireframes, FSD
| Present FSD changes to Client and obtain approval | BA, Client SMEs, Client Owner | Rebaselined FSD
| Create Low Level Design document | TL, Sr. Developer | Low Level Design (LLD)
| Review LLD | TL, Architect | Reviewed LLD
| Create Test Scenario/ Test Cases | Tester | Test Scenarios, Test Cases
| Review QA Test Scenarios/ Cases internally | BA, Test Manager | Refined QA Test Scenarios/ Test Cases
| Create GitHub Project & set up Dev/ QA environment | TL | Repository Setup, Dev/ QA Environment
| Consolidate UAT Test Scenarios (from QA artifatcs) (Optional) | BA | UAT Test Scenarios
| Plan for Application/ Model Deployment | AI/ML Engineer, DevOps Lead, Architect | Deployment Plan
Data Preparation & Engineering | Collect and Test Required Data | Data Engineer, Data Scientist | Data Set (balanced, quality assured)
| Perform Data Cleaning & Transformation | Data Engineer, Data Scientist | Cleaned Data Set
| Perform Data Annotation & Labeling | Data Scientist, Data Annotators | Labeled Data Set
| Perform Data Augmentation | Data Engineer, Data Scientist | Augmented Data Set
| Establish Data Storage & Management | Data Engineer, DevOps Lead | Data Storage Setup Report
| Conduct Data Versioning | Data Engineer, Data Scientist | Data Versioning Log
AI Model Development & Test Iterations | Perform Feature Engineering | Data Scientist, AI/ML Engineer | Updated HLD
| Perform Model Training & Hyperparameter Tuning | AI/ML Engineer, Data Scientist | Trained AI Model (incl. Transfer Learning, Model Compression, Ensemble Learning etc.)
| Evaluate Model | AI/ML Tester, Data Scientist | Evaluation Report
| Conduct Bias & Fairness Assessment | Ethics Auditor, Data Scientist | Updated Evaluation Report
| Perform Explainability Reporting | Data Scientist, Ethics Auditor | Explainability Report
Application Development & Test Iterations | Develop and unit test features as per iteration plan | Developer | Program Code
| Integrate Application Components | Developer | Integrated Program Code
| Integrate AI Model | AI/ML Engineer, Data Scientist, Developer | Integrated Program Code
| Review key code components | TL | Reviewed Program Code
| Provide Demo to BA | Developer, Tester | Feature Demo
| Deploy features in QA | TL | Updated Code Repository
| Test (system/ integration) features in QA within the iteration cycle | Tester | Test Case Tracker
| Update QA Defect Tracker | Tester | Defect Tracker
| Report test progress via Daily Dashboard | Tester, Test Manager | Daily Test Progress Dashboard
| Fix QA defects while working on other features | Developer | Updated Defects Tracker, Updated Code
| Conduct fix testing | Tester | Updated Defects Tracker
| Conduct regression test & confirm exit criteria in last iteration | Tester, Test Manager | QA Exit Report
UAT Iterations | Deploy features in UAT | TL | Updated Code Repository
| Communicate feature releases to Client | DM | UAT Release Note
| Provide Demo to UAT Users | BA, Tester | UAT Demo
| Provide Demo on AI Model to UAT Users | UAT Testers, Client SMEs | UAT Demo
| Raise UAT defects in tracker | UAT Tester | UAT Defect Tracker
| Update UAT Test Case Tracker | UAT Tester | UAT Test Case Tracker
| Triage UAT defects with Client | BA, UAT Tester | UAT Defect Tracker
| Fix UAT defects and deploy in QA | Developer | UAT Defect Tracker, Program Code
| Test UAT fixes in QA environment & confirm fixes | Tester | UAT Defect Tracker
| Deploy UAT fixes in UAT | TL | Deployed UAT Fixes
| Communicate to Client on UAT fix releases | DM | UAT Release Note
| Perform Performance test while UAT is underway | Tester, Architect | Performance Test Report
Deployment Phase | Obtain UAT sign-off from Client | DM, Client Owner | UAT Sign-Off
| Identify & conduct Regression Test after UAT sign-off | Tester | Regression Test Report, Regression Test Suite
| Update Deployment Guideline with module-specific details | TL | Updated Deployment Plan
| Provide Demo to L&D Team | BA, Learning & Development Team (L&D Team) | Feature Demo
| Create Training Materials/ User Manuals | L&D Team, BA | Training Materials, User Manuals
| Create Training Materials/ User Manuals | L&D Team, BA, DM, Client Owner | Signed-off Training Materials/ User Manuals
| Send Release Note to Client & obtain deployment sign-off | DM | Release Note, Client Deployment Sign-Off
| Deploy Application/ Module in Production | DevOps Lead | Deployed code
| Deploy AI Model in Production | AI/ML Engineer, DevOps Lead | Deployed AI Model
| Perform Sanity Test after deployment | Tester | Sanity Test Report
| Communicate module deployment to Client | DM | Deployment Confirmation Email
| Obtain sanity confirmation from Client | DM, Client Owner, Product Owner | Sanity Confirmation Mail
| Detect Model Drift and Retrain (continuous) | Data Scientist, AI/ML Engineer | Model Drift Report
Closure Phase | Plan & conduct training to Users | BA, DM, Client Owner | User Training Attendance Sheet
| Review & submit technical docs to Client | DM | Complete Technical Documents
All Phases - Task Allocation | Break-down respective stream-wise work to 4-hour tasks | BA Manager, TL, Test Manager | Task Tracker
| Allocate tasks to team members (3-days rolling basis) | BA Manager, TL, Test Manager | Updated Task Tracker
All Phases - Task Execution | Conduct working meeting within the Streams related to design, dev issues, requirement clarifications, etc. as required | All Team Members | NA
| Set-up and use Google Chat rooms for each Stream to collaborate among team members | BA Manager, TL, Test Manager | Google Chat Rooms
All Phases - Task Monitoring | Update task tracker by the end of the day | All Team Members | Task Tracker
| Update defect tracker as defects are fixed/ tested | All Team Members | Defect Tracker
| Update TL/ Manager on issues/ dependencies on assigned tasks | All Team Members | Task Tracker
| Join stand-up meeting daily at pre-defined time | BA Manager, TL, Test Manager | NA
| Present status of features progress, QA/ UAT defects, key issues, actions in Stand-up | BA Manager, TL, Test Manager | Iteration Plan & Tracker
| Capture resolution actions | BA Manager, TL, Test Manager | Iteration Plan & Tracker