## WBS
Custom Application Development Method
Phase | Activity | Participants | Tools | Deliverables | Agile Artefacts, if Different
Requirements Phase | Conduct project initiation and kickoff meetings | Delivery Manager (DM), Business Analyst (BA) |  | Kickoff Presentation
| Identify and engage key stakeholders | DM, BA |  | Stakeholder List, RACI Matrix
| Conduct stakeholder interviews and workshops | BA, Client SMEs, Client Owner |  | Stakeholder Requirements
| Elicit business requirements from stakeholders | BA, Client SMEs | Jira, Confluence | Business Requirements Document (BRD) | Epics, and User Cases
| Review and finalize BRD internally | BA, BA Manager |  | Reviewed BRD
| Obtain formal approval of BRD from stakeholders | DM, BA, Client Owner |  | Signed-off BRDs
| Identify functional and non-functional requirements | BA, Architect |  | Non-Functional Requirements (NFRs)
| Prioritize requirements with stakeholders | BA, DM, Product Owner |  | Prioritized Requirement List | Product Backlog
| Create UI Wireframes as per prioritization | BA, Architect | Figma | Draft UI Wireframes | Low-Fidelity Wireframes or Mockups
| Present Wireframes to Clients and obtain concurrence | BA, Client SMEs, Client Owner |  | Final UI Wireframes
| Document Functional Specs incl. User Stories, UI in iterations | BA, Product Owner | Jira, MS Word | Functional Specification Document (FSD) | User Stories with Acceptance Criteria
| Review and finalize FSD internally | BA, BA Manager, Architect |  | Reviewed FSD
| Create and finalize the Requirements Traceability Matrix (RTM) | BA | MS Excel | RTM Document
| Obtain formal approval of FSD from stakeholders in iterations | DM, BA, Client Owner |  | Signed-off FSDs
| Define/ Confirm change control process for requirements | DM, Change Control Board (CCB) |  | Change Control Plan
| Conduct requirements handover to design team | BA, Tech Lead (TL) |  | Handover Minutes
Design Phase | Create Architecture Document for entire application | Architect | MS Word | System Architecture Document (SRD)
| Walk-through and fine-tunning of SRD | Architect, TLs |  | Final SRD
| Create High Level Design (HLD) Document for entire application | TLs | MS Word | High Level Design (HLD)
| Walk-through and fine-tunning of HLD | Architect, TLs |  | Final HLD
| Create Test Plan including Test Strategy | Test Manager | MS Word | Test Strategy & Plan (TSP)
| Walk-through and fine-tunning of TSP | Test Manager, Architect, Tester |  | Final TSP
| Requirement (BRD/ FSD) Self Study & Walkthrough | BA, TL, Developer, Tester |  | BRD, FSD
| Apportion features to planned development iterations | TL |  | Iteration Plan & Tracker | Sprint Backlog, Sprint Goal
| Create/ update UI Wireframes & update FSD | BA, UI Developer | Figma | Updated UI Wireframes, FSD
| Present FSD changes to Client and obtain approval | BA, Client SMEs, Client Owner |  | Rebaselined FSD
| Create Low Level Design document | TL, Sr. Developer | MS Word | Low Level Design (LLD)
| Review LLD | TL, Architect |  | Reviewed LLD
| Create Test Scenario/ Test Cases | Tester | TestLink | Test Scenarios, Test Cases
| Review QA Test Scenarios/ Cases internally | BA, Test Manager |  | Refined QA Test Scenarios/ Test Cases
| Create GitHub Project & set up Dev/ QA environment | TL | GitHub | Repository Setup, Dev/ QA Environment
| Consolidate UAT Test Scenarios (from QA artifatcs) (Optional) | BA |  | UAT Test Scenarios
Development & Test Iterations | Develop and unit test features as per iteration plan | Developer | JUnit, Git | Program Code
| Review key code components | TL |  | Reviewed Program Code
| Provide Demo to BA | Developer, Tester |  | Feature Demo
| Deploy features in QA | TL | Jenkins | Updated Code Repository | Product Increment
| Test (system/ integration) features in QA within the iteration cycle | Tester | TestLink | Test Case Tracker
| Update QA Defect Tracker | Tester | Bugzilla | Defect Tracker
| Report test progress via Daily Dashboard | Tester, Test Manager | TestLink | Daily Test Progress Dashboard | Daily Scrum/Stand-Up Reports
| Fix QA defects while working on other features | Developer |  | Updated Defects Tracker, Updated Code
| Conduct fix testing | Tester |  | Updated Defects Tracker
| Conduct regression test & confirm exit criteria in last iteration | Tester, Test Manager |  | QA Exit Report
UAT Iterations | Deploy features in UAT | TL | Jenkins | Updated Code Repository
| Communicate feature releases to Client | DM |  | UAT Release Note
| Provide Demo to UAT Users | BA, Tester |  | UAT Demo
| Raise UAT defects in tracker | UAT Tester | Bugzilla | UAT Defect Tracker
| Update UAT Test Case Tracker | UAT Tester | TestLink | UAT Test Case Tracker
| Triage UAT defects with Client | BA, UAT Tester |  | UAT Defect Tracker
| Fix UAT defects and deploy in QA | Developer |  | UAT Defect Tracker, Program Code
| Test UAT fixes in QA environment & confirm fixes | Tester |  | UAT Defect Tracker
| Deploy UAT fixes in UAT | TL |  | Deployed UAT Fixes
| Communicate to Client on UAT fix releases | DM |  | UAT Release Note
| Perform Performance test while UAT is underway | Tester, Architect | JMeter | Performance Test Report
Deployment Phase | Obtain UAT sign-off from Client | DM, Client Owner |  | UAT Sign-Off | Definition of Done (DoD)
| Identify & conduct Regression Test after UAT sign-off | Tester | TestLink, Selenium, Postman, Appium | Regression Test Report, Regression Test Suite | Automated Regression Test Suite
| Update Deployment Guideline with module-specific details | TL |  | Deployment Guideline
| Provide Demo to L&D Team | BA, Learning & Development Team (L&D Team) |  | Feature Demo
| Create Training Materials/ User Manuals | L&D Team, BA | MS Powerpoint, MS Word | Training Materials, User Manuals
| Obtain formal approval of Training Materials/ User Manuals | L&D Team, BA, DM, Client Owner |  | Signed-off Training Materials/ User Manuals
| Send Release Note to Client & obtain deployment sign-off | DM | MS Word | Release Note, Client Deployment Sign-Off
| Deploy Module in Production | DevOps Lead |  | Deployed code
| Perform Sanity Test after deployment | Tester |  | Sanity Test Report
| Communicate module deployment to Client | DM |  | Deployment Confirmation Email
| Obtain sanity confirmation from Client | DM, Client Owner, Product Owner |  | Sanity Confirmation Mail | Sprint Review Notes
Closure Phase | Plan & conduct training to Users | BA, DM, Client Owner |  | User Training Attendance Sheet
| Review & submit technical docs to Client | DM |  | Complete Technical Documents | Retrospective Notes
All Phases - Task Allocation | Break-down respective stream-wise work to 4-hour tasks | BA Manager, TL, Test Manager | ProofHub | Task Tracker
| Allocate tasks to team members (3-days rolling basis) | BA Manager, TL, Test Manager |  | Updated Task Tracker
All Phases - Task Execution | Conduct working meeting within the Streams related to design, dev issues, requirement clarifications, etc. as required | All Team Members |  | NA
| Set-up and use Google Chat rooms for each Stream to collaborate among team members | BA Manager, TL, Test Manager | Google Chat | Google Chat Rooms
All Phases - Task Monitoring | Update task tracker by the end of the day | All Team Members | ProofHub | Task Tracker | Kanban Board
| Update defect tracker as defects are fixed/ tested | All Team Members | TestLink | Defect Tracker
| Update TL/ Manager on issues/ dependencies on assigned tasks | All Team Members |  | Task Tracker
| Join stand-up meeting daily at pre-defined time | BA Manager, TL, Test Manager |  | NA
| Present status of features progress, QA/ UAT defects, key issues, actions in Stand-up | BA Manager, TL, Test Manager | ProofHub | Iteration Plan & Tracker | Burn-Down Chart, Velocity
| Capture resolution actions | BA Manager, TL, Test Manager | ProofHub | Iteration Plan & Tracker